## Version history
Project Name | AOC
Project Manager
Version History
Sr. No | Version | Date | Additions/Modifications | Prepared/Revised by | Reviewed/Approved By
1 | 1 | 28th September 2020 | Integration with Bank e-Auction Portal | Neeraj Kumar Jain | Darpan kumar

## Size Estimate
QR012 Size Estimation
| Simple | Medium | Complex | Weighted Size
Weight | 1 | 3 | 5
Inputs | 0 | 0 | 2 | 10
Outputs | 2 | 0 | 0 | 2
Database Objects | 0 | 0 | 0 | 0
External Interfaces | 0 | 0 | 0 | 0
Weighted Size |  |  |  | 12
|  | Productivity | 1.6
|  | Skill set of employee | SME
| Productivity based on the employee skill set |  | 2
Estimated Effort = Size / Productivity |  |  | 6 | hrs
| Size of CR | S
[5 empty] | S | M | L
| Planning and Monitoring | 20% | 3.4286 |  | 20% | 15% | 10%
| Coding & Unit testing | 35% | 6 |  | 35% | 35% | 40%
| Testing QC ( Includes test plan, test case preperation, Review, testing, and release note preparation | 25% | 4.2857 |  | 25% | 30% | 30%
| QA | 5% | 0.85714 |  | 5% | 5% | 5%
| Devlopment Documentation (IA / Release Note / Unit test cases | 10% | 1.7143 |  | 10% | 10% | 10%
| Reviews ( Code and document review ) | 5% | 0.85714 |  | 5% | 5% | 5%
[5 empty] | 100% | 100% | 100%
|  | 100% | 17.1429
| Value added factor (R&D) | 0% | 0
| Total efforts |  | 17.1429

## Values
Component | Simple | Medium | Complex
Input Screens | No. Of fields<=5 | No. Of fields> 5 and <=10 | No. Of fields> 10
| No validation/business rules | No validation/business rules | Validation/business rules involved
| Transaction involves one data store | Transaction involves up to 3 data stores | Transaction involves multiple data stores
Output | Tabular | Form based | Nested
| No validation/business rules | No validation/business rules | Validation/business rules involved
| Transaction involves one data store | Transaction involves up to 3 data stores | Transaction involves multiple data stores
DB Objects | Transaction involves one data store | Transaction involves up to 3 data stores | Transaction involves multiple data stores
| Access | Excel | Word/text
| -------- | Migration involved | Imported files involved
External Interfaces | zero to one external interface | >1 or <=3 simple external interface | >= 3 or nested external interface